## Action Items May 2019
Item | Who | Date_done | Followup_response | Item_details
Look for gaps in by lake figures | NOCA
Look for gaps in by lake figures | MORA
Look for gaps in by lake figures | OLYM
Review for 2017 and 2018 data gaps | NOCA
2018 CCAL and ANC data entered | NOCA, CAA | 2019-05-02 |  | CAA, entered and double checked.
Review for 2017 and 2018 data gaps | MORA |  |  | 2018 CCAL data entered and verified, sent 2018 profile data to Boetch for upload
Review for 2017 and 2018 data gaps | OLYM
Update lake comments / annotations | All
SWE followup | NOCA | 2019-05-06 | Lofgren completed | Approve or revise site matches
SWE followup | MORA | 2019-05-07 | Ashley completed. Sent on 5/8 | Approve or revise site matches
SWE followup | OLYM | 2019-05-03 | Baccus completed | Approve or revise site matches
Continuous lake level data | Baccus | 2019-05-18 | Baccus sent initial data | Data sent from 2 lakes at OLYM, including reference materials.
Resolve N variables | Fradkin | 2019-05-24 | Boetsch converted remaining ueq/L to mg/L; CW reported data as NO3, CCAL as NO2+NO3. Data currently in database reflect this. | N03, N03+N02 and N03N, Boetsch forwarded email with grid of parameter by date. Per Powers: "NO3, NO3+NO2, and no3n have all been reported at different times- Is this deliberate? Are the units consistent or not (mg/L as Nitrogen vs. mg/L of whole ion)? Difference in methods between NH3 and NH4?"
Resolve N variables | NOCA, CAA | 2019-05-06 |  | Data sources and accuracy have been double checked, NO3 samples are all CWU, NO3n or NO3+N02 are CCAL, and do not overlap.
Resolve N variables | MORA | 2019-05-10 | Lofgren reviewed | Reviewed values and sent Boetsch confirmation of remaining ueq/l conversion needs.
Complete unit conversions for N variables | Boetsch | 2019-05-28 | Sent with revised outputs 6/4/2019 | Pending final response from OLYM on N variables. Only ueq/l to mg/l.
pH ranges OK? | Fradkin |  |  | Look for inconsistencies, per Powers: "These ranges are pretty wide (interesting). Is it real?"
DOC review | Archambault |  |  | Powers: "We have unrealistically high DOC in multiple lakes, a known issue that was discussed in Port Angeles meeting. But are we sure this is not a units conversion issue?"
Depth sensor question - binning vs. actual | Anyone |  |  | Binning vs. actual depth - "How important is the depth measurement from the sensor used in profiling? For now WSU crew is using “depth_bin_m" for profile depth."
Transport time table | Baccus | 2019-05-03 | Sent to Powers
Dipping info for lakes | Archambault
Info on fish gill netting & pesticides | Archambault | 2019-06-04 | Loaded to other FCA drive | Not sure if that is a viable option?
Detection efficiencies | ??? |  |  | Unsure what this item means - detection limits were provided, CCAL coverage may have been ambiguous (i.e., do the DL values from the website apply to all years? The 2016 values are the same as what is currently on the website.)
Water chemistry blanks and replicates | ??? |  |  | Need more detail on gaps for blanks and replicates
Zooplankton data sendoff | Fradkin | 2018-05-09 | Fradkin compiled and sent to Powers. | 2018 NOCA MOLA emailed to Fradkin on 5/6/2019.
Ice on / off data | Baccus | 2019-05-03 | Sent to Powers
Macroinvertebrates | Rawhouser & Lofgren |  |  | Lofgren sent MORA BMI to Rawhouser for upload
Spatial data / bathymetry | Boetsch / Beirne |  | Pending | Bathymetry, watershed, lake outline
Draft veg maps | Baccus / Beirne | 2019-05-10 | Sent to Powers | Veg maps and description created by Copass and sent by Baccus
Large woody debris | Fradkin & Baccus |  |  | Baustian is entering data in spreadsheet
Shoreline habitat | Baccus & Beirne | 2019-05-15 | Sent to Powers | Shoreline data and example maps sent by Baccus
Hoh lake data | Fradkin & Baccus
MORA profile data for 2008, 2009, 2010 | Lofgren | Done |  | MORA sent data to Boetch for upload
NOCA profile data for 2008, 2009, 2010 and 2011 correction | Archambault | 2019-05-06 |  | Emailed to Boetsch for upload.
NOCA profile data for 2018 | Arachambualt | 2019-05-06 |  | Emailed to Boetsch for upload.
Load profile data into database | Boetsch | 2019-05-29 | Sent with revised outputs 6/4/2019 | Raw data binned & formatted. Sent to Boetsch from all parks on 5/8/19
Updated solar information | Baccus | 2019-05-03 | Sent to Powers | 10-m DEM
List of non-core lakes with data | Rawhouser & Lofgren |  |  | Ash:Low priority? Do all agree? WSU?
Distance from lake bottom to Pressure Transducer | Baccus, Lofgren & Arachambualt

## Annotations
Park | Lake | Site_code | Event_year | Category/activity | Comment_date | Comment_by | Problem_desc | Explanatory_comment | Resolution
MORA | Upper Palisades | LH14 | 2007 | Lake
OLYM | Ferry |  | 2013 | Profile | 2019-05-02 | Baccus | DO missing | DO sensor membrane malfunction | None
NOCA | Bowan |  | ?? | Profile |  |  | DO impossibly high
NOCA | Lower East |  | 2016 | Profile |  |  | DO anomalous low

## Links and Info
What: | Link:
Path to project folder where copies of data shared with WSU should go: | \\inpolymfs3\NCCN\Projects\ACa02_Mtn_Lakes\Data\Distribution\Shared\NPS_FCA_2019
WSU shared Google Drive space (NPS can use as read-only): | https://drive.google.com/drive/folders/1llgd98I5RZhQbK9cGysjp61MsYjQgkFi