## Sheet1
Item | Who | Date_added | Date_done | Followup_response | Item_details
Manuscript outline | SP |  |  |  | Put together a manuscript outline for NPS review
Missing 0 / Complete 1 |  |  | July |  | Put together new missing data/complete data record for NPS review
Review recent data export |  |  | June/July |  | Review the latest (June 04) database export from John
Review fish removal data |  |  | July |  | Review fish removal/treatment data from Carmen
WRT calculations | SP | 2019-07-08
Missing early years data: is this a WSU or NPS problem? | MRB | 2019-07-08 | 2019-07-08 | This was a WSU issue. In bigjoin creation process was using merge, which did an inner_join equivalent and removed years we didn't ALSO have ice data for. Replaced with left_join. Should triple check all good now. | Records (e.g., chlorophyll pre-2011 in MORA) were missing in our plots.
Missing 2011 iceoff dates |  | 2019-07-08 |  |  | WSU should follow up with Bill, Frad, etc. on this. NPS team wasn't sure which datasets Bill had access to when building this data it seemed.
AGU abstract submission (within 1-2 weeks of July 8) | SP | 2019-07-08 | July
Zooplankton follow-up | MRB | 2019-07-08 |  |  | Look into multivariate analysis of zooplankton data. Could also investigate temp, nutrients, length of ice-free season impact on zoops (particularly for assessing cladoceran dominance)
Do work with the pressure sensor depth data |  | 2019-07-11 |  |  | We received some pressure sensor depths, so we should make sure to make progress on the lake level process.
Re-calc the physiography data we need using ArcMap |  | 2019-07-11 |  |  | John B said that the geodatabase we were given is the most accurate source of data on individual lakes. Not all lakes in the geodatabase match up with the NCCN report data so the geodatabase version is the one to go with.
Respond to Carmen RE: missing data | SP + MRB | 2019-07-25 |  |  | Carmen provided info on some of the missing data from the latest version of data1missing0 on 2019-07-25. We need to check over her points, decide if there's anything she has that we need, see if there's anything that we have that we're overlooking, and follow up with her.